## Dashboard
Hotel Capital Expenditure Budget
Property Name | Harbor View Hotel |  | Budget Year | 2026 |  | As of Date |  |  | Planning Assumptions
[9 empty] | Default Contingency Rate | 10%
[9 empty] | Internal Capitalization Threshold | 5000
Approved Budget |  | Actual Spend |  | Open Commitments |  | Forecast at Completion |  |  | Management Review Threshold | 50000
[9 empty] | Budget Warning Percentage | 90%
[9 empty] | Fiscal Year Start | 2026-01-01
Forecast Variance |  | Budget Utilization |  | Projects Requiring Attention |  | Pending Approval |  |  | Fiscal Year End | 2026-12-31
[9 empty] | Schedule Warning Days | 30
These are internal planning assumptions. Update them to match the property’s ownership, accounting, and approval policies.
Capital Category | Approved Budget | Actual Spend | Open Commitments | Forecast at Completion | Forecast Variance |  | Project Status | Count
Guestrooms | [6 empty] | Not Started
Building and Envelope | [6 empty] | In Progress
Food and Beverage | [6 empty] | Complete
Mechanical, Electrical, and Plumbing | [6 empty] | On Hold
Technology | [6 empty] | Past Due
Meetings and Events | [6 empty] | Canceled
Life Safety and Security
Site and Grounds
Projects Requiring Management Review
Project ID | Project Name | Project Owner | Approval Status | Project Status | Approved Budget | Forecast at Completion | Forecast Variance | Target Completion Date | Attention Reason

## CapEx Plan
Project ID | Project Name | Capital Category | Property Area | Project Description | Business Justification | Priority | Project Owner | Funding Source | Approval Status | Approval Date | Planned Start Date | Target Completion Date | Actual Completion Date | Original Estimate | Project Contingency Rate | Planning Estimate | Approved Budget | Actual Spend | Open Commitments | Estimate to Complete | Forecast at Completion | Forecast Variance | Budget Utilization | Project Status | Capitalization Review | Attention Flag | Attention Reason | Management Notes
CAP-26001 | Guestroom PTAC Replacement – Phase 1 | Guestrooms | Guestrooms | Replace aging PTAC units in the first guestroom phase. | Improve temperature reliability and reduce emergency repairs. | High | Director of Engineering | Replacement Reserve | Approved | 2026-01-20 | 2026-02-02 | 2026-05-29 |  | 65000 | 10% |  | 72000 |  |  | 54000 | [7 empty] | Phase one units prioritized by service history.
CAP-26002 | West Wing Roof Membrane Replacement | Building and Envelope | Roof | Replace the west wing roof membrane and damaged insulation. | Reduce water intrusion risk and protect occupied spaces. | Critical | Director of Engineering | Owner Contribution | Approved | 2026-02-12 | 2026-03-16 | 2026-06-30 |  | 170000 | 8% |  | 185000 |  |  | 12500 | [7 empty] | Final inspection and closeout allowance remains.
CAP-26003 | Main Kitchen Combi Oven | Food and Beverage | Kitchen | Replace an unreliable production oven with a combi oven. | Support banquet production and reduce equipment downtime. | High | Executive Chef | Operating Reserve | Approved | 2026-01-05 | 2026-01-12 | 2026-02-27 | 2026-02-18 | 44000 | 8% |  | 48000 |  |  | 0 | [7 empty] | Installed, trained, and accepted by culinary leadership.
CAP-26004 | Pool Circulation Pump Upgrade | Mechanical, Electrical, and Plumbing | Pool | Replace pool circulation pumps and update associated controls. | Improve reliability and maintain consistent circulation. | High | Chief Engineer | Replacement Reserve | Approved | 2026-03-10 | 2026-04-06 | 2026-05-15 |  | 29000 | 10% |  | 32000 |  |  | 3600 | [7 empty] | Commissioning and final balancing remain.
CAP-26005 | Guest Wi-Fi Access Point Refresh | Technology | Property-Wide | Refresh access points and improve coverage in guestrooms and public areas. | Improve network capacity and guest connectivity. | High | Information Technology Manager | Owner Contribution | Approved | 2026-01-28 | 2026-02-09 | 2026-07-31 |  | 87000 | 9% |  | 95000 |  |  | 8000 | [7 empty] | Final configuration and coverage testing remain.
CAP-26006 | Ballroom Carpet Replacement | Meetings and Events | Ballroom | Replace worn ballroom carpet and transition details. | Improve event presentation and address visible wear. | Medium | Director of Events | Owner Contribution | Pending |  | 2026-07-06 | 2026-08-21 |  | 100000 | 10% |  | 0 |  |  | 108000 | [7 empty] | Awaiting ownership review of final pattern and funding.
CAP-26007 | Elevator Control Modernization | Mechanical, Electrical, and Plumbing | Property-Wide | Modernize elevator controls for the two guest elevators. | Improve reliability, ride quality, and serviceability. | Critical | General Manager | Financing | Approved | 2026-04-15 | 2026-05-04 | 2026-10-30 |  | 225000 | 7% |  | 240000 |  |  | 5000 | [7 empty] | Coordinate shutdown windows with occupancy forecast.
CAP-26008 | Laundry Washer Replacement | Mechanical, Electrical, and Plumbing | Laundry | Replace two end-of-life commercial washers. | Restore laundry capacity and reduce recurring repair expense. | High | Executive Housekeeper | Replacement Reserve | Approved | 2026-01-09 | 2026-01-19 | 2026-03-06 | 2026-02-25 | 61000 | 8% |  | 66000 |  |  | 0 | [7 empty] | Equipment is operating and project closeout is complete.
CAP-26009 | Parking Lot Resurfacing | Site and Grounds | Parking | Mill, repair, resurface, and restripe primary parking areas. | Improve drainage, appearance, and pavement condition. | Medium | Director of Operations | Operating Reserve | Approved | 2026-06-25 | 2026-08-03 | 2026-09-18 |  | 125000 | 8% |  | 135000 |  |  | 120000 | [7 empty] | Forecast includes added base repair identified after mobilization.
CAP-26010 | Fire Alarm Control Panel Replacement | Life Safety and Security | Property-Wide | Replace the obsolete fire alarm control panel and related modules. | Improve system supportability and reduce failure exposure. | Critical | Director of Engineering | Owner Contribution | Approved | 2026-03-24 | 2026-04-13 | 2026-07-17 |  | 76000 | 8% |  | 82000 |  |  | 2500 | [7 empty] | Final testing documentation and training remain.
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
10%
Formulas:
Project Status = IFERROR(IF([Project ID]="","",IF([Approval Status]="Canceled","Canceled",IF([Actual Completion Date]<>"","Complete",IF([Approval Status]="On Hold","On Hold",IF(AND([Target Completion Date]<TODAY(),[Target Completion Date]<>""),"Past Due",IF(AND([Planned Start Date]<>"",[Planned Start Date]<=TODAY()),"In Progress","Not Started")))))),"")
Attention Flag = IFERROR(IF([Project ID]="","",IF(OR([Forecast Variance]<0,[Budget Utilization]>=Dashboard!$K6,[Project Status]="Past Due",AND([Planning Estimate]>=Dashboard!$K5,[Approval Status]="Pending"),AND([Project Status]="Not Started",[Target Completion Date]<>"",[Target Completion Date]-TODAY()<=Dashboard!$K9,[Target Completion Date]>=TODAY())),"Review","OK")),"")

## Spend Log
Transaction ID | Project ID | Project Name | Capital Category | Transaction Date | Vendor | Document Number | Transaction Type | Cost Description | Amount | Commitment Status | Payment Status | Funding Source | Entered By | Review Notes
TXN-260001 | CAP-26001 |  |  | 2026-02-06 | Coastal Mechanical Supply | INV-48217 | Actual | Initial PTAC unit shipment | 18000 | Not Applicable | Paid | Replacement Reserve | Capital Projects Accountant | Matched to receiving documentation.
TXN-260002 | CAP-26002 |  |  | 2026-03-20 | Atlantic Roofing Group | PO-260184 | Commitment | Roof replacement contract | 172500 | Open | Not Invoiced | Owner Contribution | Director of Engineering | Contract value excludes final closeout allowance.
TXN-260003 | CAP-26003 |  |  | 2026-02-10 | Commercial Kitchen Systems | INV-77104 | Actual | Combi oven and installation | 46500 | Not Applicable | Paid | Operating Reserve | Assistant Controller | Installation and training included.
TXN-260004 | CAP-26004 |  |  | 2026-04-10 | AquaFlow Services | PO-260231 | Commitment | Pool pump equipment and labor | 28400 | Open | Not Invoiced | Replacement Reserve | Chief Engineer | Final balancing billed separately.
TXN-260005 | CAP-26005 |  |  | 2026-02-20 | Lodging Network Solutions | INV-11382 | Actual | Network design and site survey | 15000 | Not Applicable | Paid | Owner Contribution | Information Technology Manager | Approved design phase invoice.
TXN-260006 | CAP-26005 |  |  | 2026-03-02 | Lodging Network Solutions | PO-260209 | Commitment | Access points and installation | 72000 | Open | Invoice Received | Owner Contribution | Capital Projects Accountant | Invoice under review against installation progress.
TXN-260007 | CAP-26007 |  |  | 2026-05-08 | Metro Elevator Systems | PO-260315 | Commitment | Elevator controls modernization | 235000 | Open | Not Invoiced | Financing | General Manager | Shutdown schedule requires operating coordination.
TXN-260008 | CAP-26008 |  |  | 2026-02-04 | Hospitality Laundry Equipment | INV-88219 | Actual | Two commercial washers and startup | 64200 | Not Applicable | Paid | Replacement Reserve | Executive Housekeeper | Equipment accepted after startup testing.
TXN-260009 | CAP-26009 |  |  | 2026-08-07 | Lakeside Paving Company | INV-26077 | Actual | Mobilization and site preparation | 20000 | Not Applicable | Invoice Received | Operating Reserve | Director of Operations | Invoice pending field quantity review.
TXN-260010 | CAP-26010 |  |  | 2026-04-17 | Sentinel Fire Systems | PO-260271 | Commitment | Fire alarm panel replacement | 79500 | Open | Not Invoiced | Owner Contribution | Director of Engineering | Testing and documentation included in contract.

## Instructions
Hotel Capital Expenditure Workbook Instructions
Validation Lists
Getting Started |  | Capital Categories | Property Areas | Priorities | Funding Sources | Approval Statuses | Transaction Types | Commitment Statuses | Payment Statuses
1. Update the property name, budget year, fiscal dates, and planning assumptions on the Dashboard. |  | Guestrooms | Guestrooms | Critical | Operating Reserve | Proposed | Commitment | Open | Not Invoiced
2. Enter each capital project once on the CapEx Plan. |  | Building and Envelope | Guest Corridors | High | Owner Contribution | Pending | Actual | Closed | Invoice Received
3. Assign a unique Project ID before entering transactions. |  | Food and Beverage | Lobby | Medium | Replacement Reserve | Approved |  | Not Applicable | Scheduled for Payment
4. Record purchase orders and signed contracts as commitments in the Spend Log. |  | Mechanical, Electrical, and Plumbing | Front Desk | Low | Insurance Proceeds | On Hold |  |  | Paid
5. Record incurred project costs as actual transactions. |  | Technology | Restaurant |  | Financing | Canceled |  |  | Not Applicable
6. Close a commitment when it is canceled, fully replaced by actual costs, or otherwise no longer outstanding. |  | Meetings and Events | Bar |  | Other
7. Update Estimate to Complete as project conditions and remaining work change. |  | Life Safety and Security | Kitchen
8. Review Dashboard exceptions before ownership or management meetings. |  | Site and Grounds | Ballroom
9. Do not overwrite formula columns. |  |  | Meeting Rooms
Pool
Important Definitions |  |  | Fitness Center
Original Estimate | Estimated project cost before contingency. |  | Laundry
Planning Estimate | Original estimate plus the project contingency rate. |  | Engineering
Approved Budget | Amount formally approved under the property’s internal process. |  | Roof
Actual Spend | Actual cost transactions recorded in the Spend Log. |  | Exterior
Open Commitments | Open commitment transactions recorded in the Spend Log. |  | Parking
Estimate to Complete | Expected future costs not already included in actual spending or open commitments. |  | Administrative Offices
Forecast at Completion | Actual Spend plus Open Commitments plus Estimate to Complete. |  | Property-Wide
Forecast Variance | Approved Budget minus Forecast at Completion. |  | Other
Budget Utilization | Actual Spend plus Open Commitments divided by Approved Budget.
Internal Capitalization Threshold | A user-controlled planning threshold that should match the property’s accounting policy; it is not presented as a legal standard.
Data Entry Guidance
• Do not enter the same invoice as both an open commitment and an actual cost unless the commitment is adjusted or closed to prevent double counting.
• Use one consistent Project ID across both input worksheets.
• Enter costs as positive values.
• Use Not Applicable for Commitment Status on actual transactions.
• Review red and amber cells before relying on dashboard totals.
• The workbook is a planning and tracking tool and does not replace the property’s accounting records, approval documentation, contracts, or safety review processes.