## Dashboard
Hotel Opening Readiness Dashboard
Live checklist summary for pre-opening leadership review
Total Tasks |  |  | Completed |  |  | Overall Completion
Overdue |  |  | Due in 14 Days |  |  | On Track
Planned Budget |  |  | Actual Spend |  |  | Budget Variance
Readiness by Department |  |  |  | Status Mix
Department | Tasks | Avg. Complete |  | Status | Tasks
Executive Office |  |  |  | Complete
Front Office |  |  |  | On Track
Housekeeping |  |  |  | Due Soon
Food & Beverage |  |  |  | Overdue
Engineering |  |  |  | Not Scheduled
Sales & Marketing
Finance & HR

## Checklist
Hotel Opening Master Checklist
Task ID | Phase | Department | Opening Task | Assigned Lead | Priority | Planned Start | Due Date | Completion Date | Dependency / Predecessor | Planned Budget | Actual Spend | Variance | % Complete | Status | Days to Due | Notes
OPN-001 | Planning | Executive Office | Approve opening governance calendar |  | High | 2026-06-08 | 2026-07-28 | 2026-07-26 |  | 4500 | 4300 |  | 100% |  |  | Leadership sign-off filed
OPN-002 | Pre-Opening | Engineering | Complete life-safety systems inspection |  | Critical | 2026-07-13 | 2026-08-27 |  | OPN-001 | 18000 | 17250 |  | 80% |  |  | Follow-up test is pending
OPN-003 | Pre-Opening | Front Office | Configure front desk operating procedures |  | High | 2026-07-28 | 2026-09-11 |  | OPN-001 | 6500 | 3100 |  | 65% |  |  | Night audit workflow included
OPN-004 | Pre-Opening | Housekeeping | Receive and stage opening linen inventory |  | High | 2026-08-02 | 2026-09-18 |  | OPN-001 | 42000 | 26000 |  | 55% |  |  | Final delivery scheduled
OPN-005 | Pre-Opening | Food & Beverage | Finalize restaurant opening menus |  | Medium | 2026-08-07 | 2026-10-01 |  |  | 7800 | 5200 |  | 70% |  |  | Seasonal pricing under review
OPN-006 | Pre-Opening | Sales & Marketing | Launch local opening campaign |  | High | 2026-08-17 | 2026-10-16 |  | OPN-001 | 35000 | 14000 |  | 40% |  |  | Digital and neighborhood channels
OPN-007 | Planning | Finance & HR | Complete new-hire payroll setup review |  | Critical | 2026-07-23 | 2026-09-03 |  | OPN-001 | 9000 | 8700 |  | 90% |  |  | Escalated for final verification
OPN-008 | Opening Week | Front Office | Run full guest arrival simulation |  | Critical | 2026-08-27 | 2026-09-14 |  | OPN-003 | 2500 | 0 |  | 20% |  |  | Use fictional guest profiles only
OPN-009 | Opening Week | Housekeeping | Complete model-room quality audit |  | Medium | 2026-08-29 | 2026-09-24 |  | OPN-004 | 1200 | 0 |  | 10% |  |  | Inspect all room-type standards
OPN-010 | Post-Opening | Executive Office | Conduct 30-day operating review |  | Medium | 2026-10-06 | 2026-11-05 |  |  | 3000 |  |  | 0% |  |  | Review service, staffing, and costs

## Parameters
Opening Checklist Parameters
Department | Default Assigned Lead | Assumption | Editable Value | Use
Executive Office | General Manager | Due Soon Window (Days) | 14 | Controls the Due Soon status
Front Office | Director of Front Office | Hotel Name | Harbor Point Hotel | Editable property reference
Housekeeping | Executive Housekeeper | Target Opening Date | 2026-10-21 | Planning reference only
Food & Beverage | Director of Food & Beverage | Opening Budget | 275000 | Leadership planning assumption
Engineering | Chief Engineer
Sales & Marketing | Director of Sales
Finance & HR | Director of Finance & People

## Instructions
Workbook Instructions
Sheet | Purpose | Editable Inputs | Calculated Fields | Recommended Use | Notes
Dashboard | Summarizes readiness, deadlines, budget, and department progress. | None | All KPI cards, department summaries, status counts, and charts. | Review during opening leadership meetings. | Dashboard values update from the Checklist sheet.
Checklist | Maintains the master list of opening tasks. | Gold cells: IDs, phases, departments, tasks, priorities, dates, dependencies, budgets, completion, and notes. | Assigned Lead, Variance, Status, and Days to Due. | Add tasks through row 111 and update progress regularly. | Use 100% or a completion date to mark a task Complete.
Parameters | Stores editable operating assumptions and department lead defaults. | Gold cells: lead assignments, due-soon window, hotel name, opening date, and budget. | None | Update assumptions before entering detailed tasks. | Changing department leads updates calculated assignments.
Status Logic | Explains the automated checklist status. | % Complete, Completion Date, and Due Date on Checklist. | Complete, Overdue, Due Soon, On Track, or Not Scheduled. | Use actual task evidence when entering completion. | Due Soon uses the editable day window on Parameters.
Quick Start
1. Review the hotel name, target opening date, due-soon window, and department leads on Parameters.
2. Enter or revise opening tasks in gold cells on Checklist. Keep each task specific and measurable.
3. Enter planned and actual spend in U.S. dollars. Variance is Actual Spend minus Planned Budget.
4. Update % Complete and Completion Date from documented operating evidence.
5. Review overdue and due-soon items on Dashboard during recurring pre-opening meetings.