## Dashboard
Hotel Owner Reporting Package
[5 empty] | Month | Total Revenue | Budget Revenue | GOP | Occupancy | ADR | RevPAR
Property Name | Harbor Point Hotel |  | Management Fee Rate | 3%
Reporting Month | 2026-10-01 |  | FF&E Reserve Rate | 4%
Report Preparation Date |  |  | Occupancy Target | 72%
Prepared By | Jordan Lee, General Manager |  | ADR Target | 189
Report Status | Under Review |  | Labor Cost Target | 32%
|  |  | Minimum Cash Balance | 150000
|  |  | Action Item Warning Days | 7
|  |  | CapEx Variance Warning | 10%
Selected Month Key Performance Indicators
Occupancy |  |  | GOP Margin
ADR |  |  | Net Operating Income
RevPAR |  |  | Labor Cost Percentage
Total Revenue |  |  | Ending Cash
Gross Operating Profit |  |  | Guest Satisfaction Score
Monthly Budget Variance
Metric | Actual | Budget | Variance | Variance Percentage
Total Revenue
Gross Operating Profit
Net Operating Income
Cash, Capital, and Action Summary
Ending Cash |  |  | CapEx Committed
Minimum Cash Balance |  |  | Projects Over Budget
Approved CapEx |  |  | Open Action Items
CapEx Spent |  |  | Overdue Action Items

## Monthly Performance
Monthly Hotel Operating Performance
Enter one record per month using the first day of the month. Yellow cells are inputs; gray cells are calculated.
Reporting Month | Days in Month | Rooms Available | Rooms Sold | Complimentary Rooms | Occupancy | Rooms Revenue | ADR | RevPAR | Food and Beverage Revenue | Other Operating Revenue | Total Revenue | Rooms Department Expense | Food and Beverage Department Expense | Other Department Expense | Administrative and General Expense | Sales and Marketing Expense | Property Operations and Maintenance Expense | Utilities Expense | Total Labor Cost | Total Departmental Expenses | Total Undistributed Expenses | Gross Operating Profit | GOP Margin | Fixed Charges | Management Fee | FF&E Reserve | Net Operating Income | NOI Margin | Beginning Cash | Cash Receipts | Cash Disbursements | Owner Contributions | Owner Distributions | Ending Cash | Budget Total Revenue | Budget Gross Operating Profit | Budget Net Operating Income | Revenue Variance | Revenue Variance Percentage | GOP Variance | GOP Variance Percentage | NOI Variance | NOI Variance Percentage | Prior Year Total Revenue | Prior Year Gross Operating Profit | Prior Year Net Operating Income | Guest Satisfaction Score | Report Status | Management Commentary | Financial Source Reference | Operations Source Reference
2026-01-01 |  | 3720 | 2455 | 8 |  | 421000 |  |  | 128000 | 34000 |  | 92872 | 65354 | 13759 | 56901 | 44454 | 44454 | 32006 | 184000 |  |  |  |  | 37895 |  |  |  |  | 220000 | 571340 | 530530 | 0 | 45000 |  | 588830 | 237864 | 156040 | [6 empty] | 553850 | 216876 | 142135 | 87 | Final | Weekend leisure demand exceeded budget, while weekday corporate demand remained soft. | January 2026 Operating Statement.xlsx | Monthly Rooms Summary - January 2026
2026-02-01 |  | 3360 | 2352 | 9 |  | 409000 |  |  | 121000 | 32000 |  | 91347 | 64282 | 13533 | 53952 | 42150 | 42150 | 30348 | 178000 |  |  |  |  | 36530 |  |  |  |  | 214000 | 550760 | 511420 | 0 | 20000 |  | 567620 | 228723 | 149852 | [6 empty] | 533900 | 208541 | 136499 | 88 | Final | Group banquet revenue supported food and beverage performance. | February 2026 Operating Statement.xlsx | Monthly Rooms Summary - February 2026
2026-03-01 |  | 3720 | 2753 | 10 |  | 493000 |  |  | 139000 | 36000 |  | 110741 | 77929 | 16406 | 63059 | 49265 | 49265 | 35471 | 202000 |  |  |  |  | 43420 |  |  |  |  | 208000 | 654640 | 607880 | 0 | 20000 |  | 674680 | 271181 | 177441 | [6 empty] | 634600 | 247254 | 161629 | 89 | Final | Spring booking pace improved and reduced reliance on discounted channels. | March 2026 Operating Statement.xlsx | Monthly Rooms Summary - March 2026
2026-04-01 |  | 3600 | 2772 | 11 |  | 510000 |  |  | 146000 | 38000 |  | 110554 | 77797 | 16379 | 64403 | 50315 | 50315 | 36227 | 211000 |  |  |  |  | 45110 |  |  |  |  | 202000 | 680120 | 631540 | 0 | 20000 |  | 700940 | 293770 | 196263 | [6 empty] | 659300 | 267849 | 178774 | 90 | Final | Temporary housekeeping labor increased during peak occupancy. | April 2026 Operating Statement.xlsx | Monthly Rooms Summary - April 2026
2026-05-01 |  | 3720 | 3013 | 12 |  | 578000 |  |  | 159000 | 42000 |  | 126619 | 89102 | 18758 | 76030 | 59399 | 59399 | 42767 | 231000 |  |  |  |  | 50635 |  |  |  |  | 196000 | 763420 | 708890 | 35000 | 20000 |  | 786790 | 313065 | 203779 | [6 empty] | 740050 | 285441 | 185620 | 91 | Final | Strong weekend packages supported rate and ancillary revenue. | May 2026 Operating Statement.xlsx | Monthly Rooms Summary - May 2026
2026-06-01 |  | 3600 | 3024 | 8 |  | 596000 |  |  | 166000 | 44000 |  | 133619 | 94028 | 19795 | 77376 | 60450 | 60450 | 43524 | 239000 |  |  |  |  | 52390 |  |  |  |  | 190000 | 789880 | 733460 | 35000 | 20000 |  | 814060 | 323093 | 210027 | [6 empty] | 765700 | 294585 | 191312 | 90 | Final | Utility costs increased due to warmer weather and higher occupied room nights. | June 2026 Operating Statement.xlsx | Monthly Rooms Summary - June 2026
2026-07-01 |  | 3720 | 3236 | 9 |  | 663000 |  |  | 178000 | 47000 |  | 141458 | 99545 | 20957 | 83827 | 65490 | 65490 | 47153 | 258000 |  |  |  |  | 57720 |  |  |  |  | 184000 | 870240 | 808080 | 0 | 45000 |  | 896880 | 371362 | 246642 | [6 empty] | 843600 | 338594 | 224664 | 92 | Final | Holiday and leisure demand produced the strongest monthly room revenue. | July 2026 Operating Statement.xlsx | Monthly Rooms Summary - July 2026
2026-08-01 |  | 3720 | 3162 | 10 |  | 641000 |  |  | 174000 | 46000 |  | 139947 | 98481 | 20733 | 79901 | 62422 | 62422 | 44945 | 251000 |  |  |  |  | 55965 |  |  |  |  | 178000 | 843780 | 783510 | 0 | 45000 |  | 869610 | 359192 | 238273 | [6 empty] | 817950 | 327499 | 217041 | 91 | Final | Group production remained favorable despite modest weekday softness. | August 2026 Operating Statement.xlsx | Monthly Rooms Summary - August 2026
2026-09-01 |  | 3600 | 2844 | 11 |  | 548000 |  |  | 151000 | 40000 |  | 122511 | 86212 | 18150 | 72126 | 56349 | 56349 | 40571 | 222000 |  |  |  |  | 48035 |  |  |  |  | 172000 | 724220 | 672490 | 0 | 20000 |  | 746390 | 292467 | 188837 | [6 empty] | 702050 | 266661 | 172010 | 89 | Final | Maintenance work temporarily reduced sellable inventory on several room nights. | September 2026 Operating Statement.xlsx | Monthly Rooms Summary - September 2026
2026-10-01 |  | 3720 | 2939 | 12 |  | 572000 |  |  | 158000 | 41000 |  | 122820 | 86429 | 18196 | 74016 | 57825 | 57825 | 41634 | 229000 |  |  |  |  | 50115 |  |  |  |  | 166000 | 755580 | 701610 | 0 | 20000 |  | 778710 | 318500 | 210252 | [6 empty] | 732450 | 290397 | 191516 | 90 | Under Review | Corporate negotiated demand improved; banquet pace remains under review. | October 2026 Operating Statement.xlsx | Monthly Rooms Summary - October 2026

## CapEx & Actions
Capital Expenditures and Management Actions
Capital Expenditure Projects
Project ID | Project Name | Project Category | Business Reason | Approval Date | Planned Start Date | Planned Completion Date | Actual Completion Date | Project Owner | Vendor | Approved Budget | Amount Spent | Amount Committed | Forecast Final Cost | Remaining Budget | Variance to Budget | Variance Percentage | Funding Source | Project Status | Priority | Owner Approval Reference | Latest Update | Source Document Reference
CP-2601 | Guest room corridor carpet replacement | Guest Rooms | Replace worn corridor finishes | 2026-01-15 | 2026-02-02 | 2026-03-20 | 2026-03-18 | General Manager | Coastal Interiors | 185000 | 179500 | 0 |  |  |  |  | Reserve Account | Completed | High | OWNER-2026-01 | Installation completed below approved budget. | Carpet Contract 2026.pdf
CP-2602 | Chiller compressor replacement | Building Systems | Restore reliable cooling capacity | 2026-03-05 | 2026-05-01 | 2026-09-25 |  | Chief Engineer | Metro Mechanical | 92000 | 48000 | 56000 |  |  |  |  | Owner Contribution | In Progress | Critical | OWNER-2026-03 | Revised compressor lead time may affect completion. | Chiller Proposal Rev 3.pdf
CP-2603 | Lobby seating refresh | Public Areas | Improve arrival experience and seating condition | 2026-02-10 | 2026-04-01 | 2026-06-10 | 2026-06-06 | General Manager | Harbor Design Group | 46000 | 43800 | 0 |  |  |  |  | Operating Cash | Completed | Medium | OWNER-2026-02 | Furniture installed and final invoice recorded. | Lobby Furniture Invoice.pdf
CP-2604 | Guest Wi-Fi access point upgrade | Technology | Improve coverage on upper guest-room floors | 2026-05-12 | 2026-07-10 | 2026-10-15 |  | Chief Engineer | Atlantic Network Services | 68000 | 29000 | 34000 |  |  |  |  | Reserve Account | In Progress | High | OWNER-2026-05 | Coverage testing is underway on floors eight through ten. | Wi-Fi Upgrade Scope.xlsx
CP-2605 | Kitchen walk-in cooler repair | Food and Beverage | Address compressor cycling and temperature instability | 2026-04-18 | 2026-04-22 | 2026-09-12 |  | Food and Beverage Director | City Refrigeration | 24000 | 16500 | 6200 |  |  |  |  | Operating Cash | On Hold | High | OWNER-2026-04 | Work paused pending replacement component availability. | Cooler Repair Work Order.pdf
CP-2606 | Pool deck furniture replacement | Exterior | Replace damaged seasonal furniture | 2026-06-08 | 2026-08-01 | 2026-10-05 |  | General Manager | Suncoast Furnishings | 38000 | 17000 | 18000 |  |  |  |  | Operating Cash | In Progress | Medium | OWNER-2026-06 | First shipment received; remaining pieces are scheduled. | Pool Furniture PO.pdf
CP-2607 | Laundry equipment replacement | Building Systems | Replace inefficient washer and reduce downtime |  | 2026-11-01 | 2026-12-15 |  | Executive Housekeeper | Commercial Laundry Systems | 74000 | 0 | 0 |  |  |  |  | To Be Determined | Awaiting Approval | High | PENDING-2026-07 | Owner review requested after updated operating-cost analysis. | Laundry Replacement Analysis.xlsx
CP-2608 | Parking lot lighting upgrade | Life Safety | Improve nighttime visibility and reduce outages | 2026-07-14 | 2026-09-01 | 2026-11-20 |  | Chief Engineer | Brightway Electric | 12000 | 3500 | 6900 |  |  |  |  | Reserve Account | Approved | Medium | OWNER-2026-07 | Materials ordered; field work will begin after delivery. | Lighting Quote 2026.pdf
Management Action Items
Action ID | Reporting Month | Area | Action Item | Assigned To | Date Assigned | Due Date | Completed Date | Priority | Progress Percentage | Calculated Status | Owner Visibility | Latest Update | Related CapEx Project ID | Source Meeting Reference
ACT-2601 | 2026-08-01 | Revenue Management | Review weekday corporate rate strategy. | Revenue Manager | 2026-08-17 | 2026-09-03 |  | High | 45% |  | Include in Owner Report | Corporate account production review remains incomplete. |  | August 2026 Owner Meeting
ACT-2602 | 2026-08-01 | Capital Projects | Obtain a revised proposal for the chiller compressor replacement. | Chief Engineer | 2026-08-23 | 2026-09-10 |  | Critical | 70% |  | Include in Owner Report | Vendor is revising freight and crane allowances. | CP-2602 | August 2026 Owner Meeting
ACT-2603 | 2026-08-01 | Rooms | Reduce housekeeping overtime through schedule adjustments. | Executive Housekeeper | 2026-08-12 | 2026-08-29 | 2026-08-28 | High | 100% |  | Include in Owner Report | New staffing grid implemented and reviewed. |  | August 2026 Operations Review
ACT-2604 | 2026-09-01 | Food and Beverage | Finalize fall group banquet menus. | Food and Beverage Director | 2026-08-29 | 2026-09-12 |  | Medium | 65% |  | Include in Owner Report | Pricing review is scheduled with Sales and Finance. |  | September 2026 Owner Meeting
ACT-2605 | 2026-08-01 | Engineering | Investigate recurring guest room hot-water complaints. | Chief Engineer | 2026-08-07 | 2026-08-25 |  | Critical | 35% |  | Include in Owner Report | Riser balancing tests identified two floors requiring adjustment. |  | August 2026 Guest Experience Review
ACT-2606 | 2026-08-01 | Finance | Reconcile reserve-account activity for the owner statement. | Director of Finance | 2026-08-22 | 2026-09-24 |  | High | 55% |  | Include in Owner Report | Two capital invoices remain under review. |  | August 2026 Owner Meeting
ACT-2607 | 2026-09-01 | Guest Experience | Complete the guest Wi-Fi coverage test. | Chief Engineer | 2026-09-01 | 2026-09-11 |  | High | 40% |  | Include in Owner Report | Testing completed on six of ten guest floors. | CP-2604 | September 2026 Technology Review
ACT-2608 | 2026-09-01 | Finance | Update the 90-day cash forecast. | Director of Finance | 2026-09-02 | 2026-09-26 |  | Medium | 25% |  | Include in Owner Report | Forecast assumptions are being refreshed for group deposits. |  | September 2026 Owner Meeting
Formulas:
Approved Budget = IFERROR(IF([Business Reason]="","",IF([Actual Completion Date]<>"","Completed",IF([Planned Completion Date]<TODAY(),"Overdue",IF([Planned Completion Date]<=TODAY()+Dashboard!$E9,"Due Soon","Open")))),"")

## Instructions
Owner Reporting Package Instructions
Monthly Workflow
| 1 | Copy the workbook before beginning a new reporting cycle.
| 2 | Update the editable assumptions and reporting controls on the Dashboard.
| 3 | Enter the new month’s operating and cash results in Monthly Performance.
| 4 | Confirm that rooms sold does not exceed rooms available.
| 5 | Reconcile total revenue and major expense categories to the property’s internal financial reports.
| 6 | Update capital project spending, commitments, completion dates, and management comments.
| 7 | Review action-item due dates and mark completed items with a completed date.
| 8 | Review Dashboard alerts, budget variances, cash levels, and trend charts.
| 9 | Change Report Status to Final only after internal review.
Input Guidance
| 1 | Yellow cells are editable assumptions, report controls, or table inputs.
| 2 | Gray cells contain formulas and should not be overwritten.
| 3 | Reporting Month should use the first day of each month.
| 4 | Amount Spent should reflect recorded cost to date.
| 5 | Amount Committed should reflect approved but not yet recorded commitments.
| 6 | Source-reference fields are for file names or report references; they do not import data.
| 7 | Management commentary should explain significant business drivers rather than merely repeat the numbers.
Quality-Control Checklist
| Review | Reporting month selected.
| Review | Actual results entered.
| Review | Budget results entered.
| Review | Prior-year results entered.
| Review | Cash activity reconciled.
| Review | Management fee and reserve assumptions reviewed.
| Review | CapEx updates completed.
| Review | Overdue action items reviewed.
| Review | Dashboard alerts investigated.
| Review | Report status approved.